## Slide 1
ABIA STATE CSS FARMS TRAINING INITIATIVE
SUPERVISION REPORT FROM THE
17 LGAs OF ABIA STATE
MINISTRY OF AGRICULTURE

## Slide 2: Introduction - Abia State overview
4.8m
State population (2022)
Igbo
Major language
6,320
Total landmass (sq km)
49%
% of Male
51%
% of Female
17
Local Government
Areas (LGAs)
Abia State is bordered by South-Eastern and South-Southern States of Anambra, Ebonyi, Enugu, Imo, Cross River, Akwa Ibom and Rivers.
Abia State
Key
Map of Nigeria
South East, Nigeria
Geopolitical Zone
Key highlights
3
Agricultural zones, namely:
Aba (Abia South), Ohafia (Abia North) and Umuahia (Abia Central).
2
Climatic seasons: the rainy and dry seasons; Predominantly Rain forest vegetation agro-ecology
1991
Year of Creation
Umuahia
Capital City

## Slide 3
In a bid to promote economic prosperity through focused job creation and youth empowerment in agriculture, His Excellency, the Executive Governor of Abia State, Dr. Alex Chioma Otti (OFR) initiated the training of three hundred and two (302) Abia youths on various components of agriculture at CSS farms, Nasarawa State. Selection was based on a mix of criteria:
  - 184 from the 184 wards – Abia Arise
  - 17 from Mayors
  - 2 from ADP
  - 64 from Fed and State House members
  - 35 Executive Discretion
Two hundred and ninety-eight (298) of these youths who presented business plans were duly empowered to implement what they were trained on through the disbursement of interest-free loans totaling N576.7m.
A five-man committee was formed by the Honorable Commissioner of Agriculture, to conduct a supervision exercise to assess the level of implementation of the programme in 184 wards of the state from March, 2025 – June, 2025.
A state-wide supervision exercise was conducted to determine the level of implementation and compliance on the part of the beneficiaries.
Abia State CSS Farms Project Initiative
3

## Slide 4
4
Summary Statistics
Sex | Enterprise |  |  |  |  | Total
 | Livestock/Poultry | Fish Farming | Open field | Value addition | Green house | 
Male | 82 | 41 | 60 | 32 | 4 | 219
Female | 24 | 16 | 22 | 12 | 5 | 79
Total | 106 | 57 | 82 | 44 | 9 | 298

## Slide 5
5
Chart: 
| Livestock/Poultry | Fisheries | Open field | Value addition | Green house
 | 106 | 57 | 82 | 44 | 9
Summary Statistics

## Slide 6
6
Beneficiaries Availability
Chart: 
| No. of Beneficiaries
Presented | 268
Refused to Present | 26
ill-Health | 4
Assessment | No. of Beneficiaries | %
Presented | 268 | 89.93%
Refused to Present | 26 | 8.72%
ill-Health | 4 | 1.34%
Total | 298 | 100.00%

## Slide 7
7
Beneficiaries Compliance Rating
Chart: 
| No. of Beneficiaries
Very High Compliance (5) | 60
High Compliance (4) | 111
Fair Compliance (3) | 75
Low Compliance (2) | 13
Zero/No Compliance (0) | 5

## Slide 8
S/N | Name of beneficiaries | LGA | Remarks
1 | Ejike Ebere | Ugwunagbo | Reported Sick (Diabetics Complications)
2 | Ekuru-Bob Henry Nwabueze | Umuahia South | Sick with kidney problem, has been in and out of hospital.
3 | Awomukwu Angela C. | Isialangwa North | Reported sick
4 | Njoku Nehemiah | Arochukwu | Reported sick with 2 kidney stones
THE FOLLOWING BENEFICIARIES COULD NOT PRESENT THEMSELVES FOR ASSESSMENT DUE TO HEALTH CHALLENGES
Regrettably, we received a report of the demise of two beneficiaries; Mrs. Chinonye I. Egbulefu from Ikwuano LGA and Mr. Ejike Ebere from Ugwunagbo LGA
Abia State CSS Farms Project Initiative
8

## Slide 9
Abia State CSS Farms Project Initiative
9
CSS AMOUNT
ALLOCATION
BY LGA
LGA | No. of Beneficiaries | Amount Received
Aba North | 14 | 28,229,625.00
Aba South | 19 | 34,342,500.00
Arochukwu | 22 | 36,752,500.00
Bende | 16 | 29,315,000.00
Ikwuano | 18 | 30,752,500.00
Isialangwa North | 22 | 42,670,000.00
Isialangwa South | 27 | 53,000,000.00
Isuikwuato | 12 | 25,605,000.00
Obingwa | 12 | 24,662,500.00
Ohafia | 21 | 45,562,500.00
Osisioma | 19 | 39,110,000.00
Ugwunagbo | 12 | 21,150,000.00
Ukwa East | 11 | 21,790,000.00
Ukwa West | 10 | 20,062,500.00
Umuahia North | 26 | 50,960,000.00
Umuahia South | 18 | 38,292,500.00
Umunneochi | 17 | 31,070,375.00
Abia ADP | 2 | 3,372,500.00
Total | 298 | 576,700,000.00

## Slide 10
Abia State CSS Farms Project Initiative
10
CSS AMOUNT
ALLOCATION
BY LGA
LGA | No. of Beneficiaries | No. of active Incubatees
Aba North | 14 | 28
Aba South | 19 | 58
Arochukwu | 22 | 41
Bende | 16 | 35
Ikwuano | 18 | 30
Isialangwa North | 22 | 50
Isialangwa South | 27 | 52
Isuikwuato | 12 | 20
Obingwa | 12 | 26
Ohafia | 21 | 46
Osisioma | 19 | 34
Ugwunagbo | 12 | 7
Ukwa East | 11 | 13
Ukwa West | 10 | 10
Umuahia North | 26 | 43
Umuahia South | 18 | 44
Umunneochi | 17 | 28
Abia ADP | 2 | 0
Total | 298 | 565

## Slide 11
11
S/N | Challenges | Observations | Recommendation(s)
1 | Some wards/farms were hard-to-reach areas, making it very difficult and more expensive to visit | Some of the beneficiaries were politically engaged and/or involved in some other businesses which led to their little or non-compliance to the programme | The government should target unemployed youths (who are interested in agricultural enterprises) and young farmers rather than politicians (Abia Arise Members) in subsequent programmes like this.
2 | Multiple visitations to some LGAs due to unavailability of some beneficiaries on the scheduled visit days | Many of the trainees that were to be trained by the trained beneficiaries were residing far from the farm location, making it impossible for them to be trained. The reason being that the trainees were politically selected by their sponsors and not by the farmer himself. | 
3 | Some of the beneficiaries were very rude and were not cooperative to the supervisory team | Some of the beneficiaries saw this loan as grants rather than a loan to be paid back, making them nonchalant to the investment of the loan into agricultural business/enterprise as agreed | 

## Slide 12
PICTORIAL REPRESENTATION OF ABIA STATE CSS FARMS TRAINEES PROJECT SUPERVISION ACCORDING TO LGA

## Slide 13
Open field beneficiaries in their cassava/maize farm in Ehere
A beneficiary in goat and broiler enterprise
A beneficiary in fisheries enterprise with adult fish and juveniles
Aba North

## Slide 14
A beneficiary with ready-for-market birds and few days old chicks (top right) in brooding pen
An open field beneficiary posing in front of her cassava/maize/egusi farm
A beneficiary in value addition (Garri processing)
A beneficiary with matured birds ready for sale
Aba South

## Slide 15
A beneficiary showing his newly bought pumping machine to the team, the machine is been use to irrigate the farm
A beneficiary in poultry enterprise and also sales accessories use in poultry farming
Another beneficiary in Arochukwu rearing broilers.
Arochukwu

## Slide 16
Open field beneficiaries in Bende, showing their rebust and health crop farms
A well ventilated, spaced layers farm in Item
A well-built pond with healthy fish in Ngu owed by one of the beneficiaries
A beneficiary in his water melon farm in Ozuitem
Bende

## Slide 17
From left-right: a proud and happy beneficiary showcasing her matured birds in Omuhu, a newly constructed earthen pond owned by a beneficiary in Ekpiri, a beneficiary in his piggery farm in Amawom and an open field beneficiary with the Director of CSS farms and his team in Oboni ikpa.
Ikwuano

## Slide 18
This beneficiary is into integrated farming and also produces liquid eco-friendly fertilizer and insecticide using plant leaves
A beneficiary in his poultry farm with few weeks old chicks
A pig farm owned by the beneficiary with a boar, sow and piglets
Another poultry farmer beneficiary with his healthy birds
Isialangwa North

## Slide 19
A pig farm owned by one of the beneficiary in Obiakabi
A beneficiary showing his pepper nursery to the Director and his team
An open field beneficiary (in polo and black short) with the supervisory team.
Isialangwa South

## Slide 20
A beneficiary (female) with the supervisory team and her few days old chicks under brooding
Another poultry farmer beneficiary with about 3 weeks old birds
Isuikwuato

## Slide 21
A beneficiary posing with his tarpaulin fish pond teeming with fish
Open field beneficiaries in Maboko Amairi, Akumaimo and Umu Dosi showing their healthy crop farms
Obingwa

## Slide 22
A beneficiary posing in her broilers and layers farm in Ihenta
A broiler farm owned by one of the beneficiary in Ututu, ready for market
A beneficiary in his broiler farm in Ohafia
Ohafia

## Slide 23
One of the few beneficiaries in green house been assessed by the Director.
The Director and his team with a beneficiary in his pepper and ugu farm in Oso-okwa.
A beneficiary in her cassava farm in Umuakpara
Osisioma

## Slide 24
From left to right: a poultry farm in Asa-Umunka with matured birds, open field beneficiaries in their maize/cassava farms in Asa Amanhie, Asa Umunka and Umu Aja, respectively.
Ugwunagbo

## Slide 25
A rice field owned by a beneficiary, Christian Nweke and Sons
A pond filled with fish in Ohuru
Open field beneficiaries been assessed by the supervisory team in Obohia and Ikwueke, respectively.
Ukwa East

## Slide 26
A beneficiary with his birds in Uzuaku
A beneficiary (middle) with the supervisory team in her pepper farm
Another beneficiary in his poultry farm
Ukwa West

## Slide 27
A beneficiary posing in front of his poultry farm in Umuire
An open field beneficiary in his sweet potatoes' enterprise
Another beneficiary in fishery enterprise
A beneficiary showing her fish pond filled with fish to the supervisory team
A value addition beneficiary, processing unripe plantain into flour
Umuahia North

## Slide 28
A beneficiary with a well constructed pond with robust and healthy fish in Amakama
Pig farmer with over 50 piglets in Umuahia
Poultry farm in Ubakala
Another pig farmer (in black shirt) with the supervisory team
Umuahia South

## Slide 29
A beneficiary from Umunneochi showing his cassava processing enterprise located in Umudike, Umuahia
An open field beneficiary with the supervisory team in his cassava/maize/yam farm
Another open field beneficiary (white top) with the team
A poultry farmer (layers) beneficiary (Green top)
Umunneochi

## Slide 30
30
S/N | Name of Beneficiaries | Phone No | LGA | Enterprise | Address
1 | Njoku Stanley Ogburubi | 08039519252 | Aba North | Poultry | Ogbor/Ogbor II Ward 11
2 | Precious Ugoeze Agua | 08065219840 | Osisioma | Poultry | Umumgbede
3 | Ehumadu Bertha Eziuche | 08036134625 | Osisioma | Value Addition (Poultry feed production) | Umuocham/Osisioma ward 3
4 | Ejike Tochukwu U. | 08067074725 | Ugwunagbo | Poultry | Amaoji/ Uzougwu 5
5 | Chimuanya Marvis Okwudiri | 08036330932 | Ukwa East | Poultry | Ohanku/ Ikwuori 3
THE FOLLOWING BENEFICIARIES AS AT THE TIME OF VISIT, WERE YET TO START UP THEIR ENTERPRISE

## Slide 31
31
THE FOLLOWING BENEFICIARIES REFUSED TO PRESENT THEMSELVES FOR SUPERVISION
S/N | Names of Beneficiaries | LGA | Phone No. | Contact address | Sponsors
1 | Okoko Amaranna Patrick | Arochukwu | 09066427974 | Ozu Abam/78 St. Michael Road Aba | 
2 | Kalu Sunday | Arochukwu | 08059661080/ 07084735888 | Obimba Auth. Community, Iheosu-Isu/ Igwebuike Ward 7 | 
3 | Okoroafor Godswill Nwabueze | Arochukwu | 07033177095/08037071600 | 5 Frank Ibe Drive, Isialama Afaraukwu, Umuahia | 
4 | Okoro Chukwu- ebuka Miracle | Arochukwu | 081384475509/07038656321 | B4A Ehimiri Hosing Estate, Umuahia | 
5 | Osondu Nnamdi | Ikwuano | 08066521467 | Nchara Oloko | 

## Slide 32
32
THE FOLLOWING BENEFICIARIES REFUSED TO PRESENT THEMSELVES FOR SUPERVISION
S/N | Names of Beneficiaries | LGA | Phone No. | Contact address | Sponsors
6 | Chiedozie Godswill Egbe | Ikwuano | 07025071210 | Egbe’s Compound Ogbuebule, Oboro | 
7 | Awuwa Lucky Chibuikem | Ikwuano | 08032537607/08051381058 | Umuagu Ibeku Umuahia North | 
8 | Ezegbe Chinyere Peter | Ikwuano | 07037125986 | 21 Igbo Street, Umuahia | 
9 | Kingsley Ikechukwu Okoebue | Isialangwa North | 08038503664 | Eziama Nsulu/ Ward 3 | 
10 | Ifeanyi Ransom Okereke | Isuikwuato | 07032387381/09068965190 | Umuchioke, Akpukpa Uturu/ Ward 8 | 

## Slide 33
33
THE FOLLOWING BENEFICIARIES REFUSED TO PRESENT THEMSELVES FOR SUPERVISION
S/N | Names of Beneficiaries | LGA | Phone No. | Contact address | Sponsors
11 | Nwachukwu Uzochim P. | Obingwa | 08103525262 | 14 Zerock Street Aba, Abia State | 
12 | Ume Onu Enyinnaya | Ohafia | 07062204389 | 3 Oba Elu Road, Elu Ohafia | 
13 | Arunsi Ukoha Kalu | Ohafia | 08101218459 | 9 Ota Okoro Lane, Okagwe, Ohafia | 
14 | Chike Peter Igwe | Ohafia | 07032118263 | No 85 Arochukwu Road Amaekpu Ohafia | 
15 | Azubuike Kelechi | Osisioma | 08057437045/07010923238 | Ozigara Azubuike’s Compound, Okpu-Umuobo village | 

## Slide 34
34
THE FOLLOWING BENEFICIARIES REFUSED TO PRESENT THEMSELVES FOR SUPERVISION
S/N | Names of Beneficiaries | LGA | Phone No. | Contact address | Sponsors
16 | Chioma Orji | Osisioma | 08024048247/ 08088111110 | Umuekpe Village | 
17 | Ogbuka L. Ugonwanyi | Ugwunagbo | 08067243440/ 08113377775 | 9 Umuode Road, WBH Abayi, Aba/ Amorji Ihie-Iyi, Ugwunagbo | 
18 | Nwankpa Martins | Ugwunagbo (His farm is located in Taraba state. | 08134411209 | 96B Aba-Owerri Road, Aba | 
19 | Chikamnele Hossanna C. | Ugwunagbo | 08086443711 | 56 Umuagbai Road, Aba/ Amuzi Ihie | 
20 | Uko ThankGod Chukwuemeka | Umuahia North | 09066954725/ 08167295293 | Nkweogwu, Umuahia | 

## Slide 35
35
THE FOLLOWING BENEFICIARIES REFUSED TO PRESENT THEMSELVES FOR SUPERVISION
S/N | Names of Beneficiaries | LGA | Phone No. | Contact address | Sponsors
21 | Chukwunonso Udonsi | Umuahia North | 09011348236 | Road 040 WBHE Umuahia | 
22 | Austin Ikeji | Umuahia North | 07032799079 | Umuagbom Umukabia, Ohuhu | 
23 | Egwu Chinwenwa Jessica | Umuahia South | 09054734618/ 09071998596 | 100 Carmoon Street by Enugu Road/ Agbama Olokoro | 
24 | Jeremiah Dearest | Ukwa East | 08134413482/ 09044282015 | Obuozu Ndoki, Ukwa East | 
25 | Nwogu Raphel | Ukwa East | 08034858201 | Umuokoroaja Obohia-Ndoki, Ukwa East | 
26 | Nwankwo Emeka K. | Ukwa West | 09068749709 | Umuram, Ogwe Ukwa West | 

## Slide 36: Prayers
Roll over all the loans for the 259 performing (scores 2 to 5) beneficiaries for one full year
Reward those in the upper 3 performance categories as follows:
First category (60) – Enhance loan amount by 50%, implication = N53.6m
Second category (111) – 30% enhancement to loan amount; implication = N65m
Third category (77) – 20 % additional loan; implication = N29m
Poor performance: carry out in-depth situation analysis to determine if/type of further intervention needed.
Sanction the deviants as follows:
Zero performance – demand full recovery of loan amount
Those that failed to present for assessment – revisit and assess
Those that refused to be assessed:
Pursue recovery,
Invoke the GSI (global standing instruction) clause in the loan agreement;
Enforce through their sponsors
Blacklist against future state benefits
Extend N1m flat empowerment interest-free loan to all the certified incubatees
Extend program to other Abians collaborating with MOUAU ABIC. Ok but revisit and evaluate infrastructure.
Working with the PPP/IPO, collaborate with CSS Farms or any other similarly credible Company/co-investor (possibly from the prospective investors pool) to set up similar large scale integrated farm in Abia state with significant government funding.
Abia State CSS Farms Project Initiative
36

## Slide 37: Thank You